## Sheet1
Phase | Function | Start Date | End Date
1 | Pre-Planning | 2021-05-15 | 2023-05-15
Group Leaders -
Select reunion dates with DAA
Select reunion planning Chair & Reunion Committee
Select regimental and company reps
2 | Hotel, Tentative Agenda & Memorabilia Selection | 2022-05-15 | 2023-05-15
Choose event hotel HQ (Alumni Events & Chair)
Negotiate and contract with event hotel HQ (Alumni Events &Chair)
Tentative agenda prepared & reviewed (Alumni Events & Chair)
| Hotel block(s) open for reservations (Alumni Events & Chair) | 2023-05-01 | ?
| Memorabilia selection (Memorabilia Coordinator, Chair & | 2023-08-15 | 2023-12-15
Alumni Events)
3 | Detailed Planning & Memorabilia Order | 2023-12-15 | 2024-02-15
Finalize agenda (Alumni Events & Chair)
Coordinate logistics (Alumni Events)
Approve budget (Alumni Events creates, Chair approves)
| Open Registration (Alumni Events creates, Chair approves) | 2024-03-01 | ?
| Memorabilia order | 2023-12-15 | 2024-02-15
4 | Registration Open | 2024-03-01 | 2024-05-01
Monitor registration (Alumni Events & Chair)
5 | Event Execution | 2024-05-01 | 2024-05-22
Final coordination & event execution (Alumni Events & Chair)
6 | Post Event Wrap Up | 2024-05-22 | 2024-07-22
Process late additions & refunds (Alumni Events)
Post-event survey (Alumni Events & Chair)
Post-event shipping
Receive, review and pay invoices
Financial wrap up