HEADQUARTERS

United States Corp of Cadets

United States Military Academy

West Point, NY 10996

16NOV2006

# USCC OPERATION ORDER 2006-033, 500TH NIGHT 2007

Task Organization: Second Regiment is Sponsor Regiment with Class Officers in support

1.   SITUATION.  Friendly forces.  USCC conducts 500th Night activities for all second class cadets on Saturday, 20 JAN 2007. Parents and guests of the Class of 2008 will have an opportunity to visit with cadets, tour the installation, and participate in the several 500th Night activities.

2.   MISSION. USCC will conduct 500th Night activities on Saturday, 20 JAN 07 at the United States Military Academy in order to celebrate the milestone achieved by the Class of 2008 and provide an opportunity for the social development of the Class.

3.	EXECUTION.

a.  Commander’s Intent:

Purpose.  To provide the Class of 2008 and their families with a memorable event that allows maximum interaction between the Class and their guests while furthering the social development of the Class.

Key Tasks

- Effective command and control throughout the evening to ensure coordinated effort and timely execution of all tasks.

- Heightened awareness of safety and security issues given the expected arrival of approximately 1500 visitors.

- Proper coordination between all supporting USMA and USCC agencies.

- Professional, enjoyable banquet with guest speaker

- An efficient receiving line and an enjoyable hop

Endstate

  - Safe, memorable, and professionally executed event for the Class of 2008

b.	Concept of operations.  This is a 2-phased operation.  Master schedule of events is listed in coordinating instructions.

(1)  Phase I - Planning and Preparation.  This phase begins with publication of the USCC OPORD and ends with the Commandant’s Reception on Saturday, 20 1730 JAN 2007.

(2)  Phase II - Formal Banquet and Hop.  This phase begins with the Commandant’s Reception on Saturday, 20 1730 JAN 2007 and ends with the completion of the hop at 21 0030 JAN 2007.  Key tasks include the banquet, remarks from the guest speaker, a formal receiving line at Eisenhower Hall, and the hop.

c.	Tasks to maneuver units.

(1)  USCC S3.

(a)  Overall responsible for the planning and coordination of this event.

(b)  Schedule and coordinate with USAG and DOPS and all participating USCC agencies for support of 500th Night events.

(c)  Coordinate with class advisor and ISD for development and posting of a web based information signup to gather information from second class cadets regarding VIPs, handicapped parking requirements.  Ensure BTD provides VIP information to USMA Protocol Office.

(d)  Ensure for the setup of flags for the formal banquet in the Cadet Mess and the receiving lines at Eisenhower Hall. Setup flags NLT 20 1400 JAN 2007 for the rehearsal.

(e)  ICW 2nd Regiment, coordinate with the respective USMA Superintendent, Dean, and Commandant offices for receiving line structure and composition.

(2)  Brigade Tactical Department.

(a)  Supervise Corps of Cadets’ planning and execution of 500th Night.

(b)  Publish Second Class Privilege guidance.

(c)  Provide DCA and USMA Protocol Office with names of VIPs NLT 10 JAN 07 - rank of 06 (P) or the civilian equivalent based on web based sign up information given by cadets.

(d)  Provide 5 cadets to assist USCC S4 with North Area VIP parking from 1700-1900, Saturday, 20 JAN 2007.  Cadets will not be second class cadets.

(e)  Provide 4 ushers at the entrances of the Cadet Mess to assist latecomers to the banquet to find their tables on 20 1830-1930 JAN 2007. Provide the ushers with the final seating diagrams prepared by DCA. Cadets will not be 2CL cadets.

(f) Ensure chain access to the Apron (Mac statue) is unlocked NLT Saturday, 20 1700 JAN 07 to allow access to distinguished guest vehicles.

(g) Be prepared to provide cadet escorts for official guests. Escort requirements will be determined and coordinated by the Cadet Hostess Office NLT Wednesday, 10 JAN 2007.

(h)  Provide 5 ushers at Eisenhower Hall in order to facilitate movement to the hop and assist DCA with any contingencies. Ushers will report to DCA (Mr. Oldham) NLT 20 1900 JAN 2007.

(i)  Coordinate USCC S4 for handicapped passes and distribute to cadets through the company TAC teams. Ensure 2CL cadets understand this process and work these issues through BTD only.

(j)  Ensure completion of the second class web based information signup that will close NLT COB on Wednesday, 10 JAN 07.

(l) Ensure second class cadets are properly prepared and informed of all aspects of 500th Night.

(3)  2nd Regiment.

(a)  Serve as Sponsor Regiment for 500th Night. Responsibilities include C2 for the rehearsal and execution of the banquet and hop and assist USCC S3 in the planning and coordination of this event. BPT brief the Commandant on all 500th Night activities.

(b) Coordinate and liaison with the guest speaker.

(c)  Ensure that the Class Committee coordinates with DCA and the Cadet Hostess for purchase and engraving of a gift for the guest speaker, the seating plan, script, and programs.

(d)  Provide 4 TAC or TAC NCOs to control movement into the receiving lines at Eisenhower Hall.

(e) Conduct banquet rehearsal 20 1400 JAN 2007.

(g)  Develop and execute plan for the receiving line structure and composition prior to the hop.

(f)  ICW USCC S3, coordinate with the respective USMA Superintendent, Dean, and Commandant offices for reception personnel.

(4)  USCC S4.

(a)  Supervise the North Area parking plan for the Commandant’s official guests and the handicapped on Saturday, 20 JAN 2007 from 1700-1900. Brief parking detail on parking plan requirements.

(b)  ICW DCA (POC Mr. Oldham), provide sample parking passes to the Provost Marshal and USMA security guards via DPTMS (Mr. Peddy).

(c)  Provide handicapped parking passes to BTD for distribution to cadets.

(d) In support of DCA, help coordinate with USAG for the transportation and parking plan for 500th Night.

(5)	USCC SGS.

(a)  Prepare the Commandant to conduct the Commandant’s Reception on Saturday, 20 1730-1830 JAN 2007 in Quarters 101. Determine size and composition of attendees.

(b)  Prepare for the Commandant’s participation in the 500th Night banquet and receiving line.

(6)  DCA.

(a)  Coordinate with 2nd Regiment for planning and executing the formal banquet and hop on Saturday, 20 JAN 07.

(b) Coordinate with USAG for transportation and parking plan 500th Night. Coordinate with DPTMS and DES for parking and traffic control support. Submit USMA form 1-189, transportation request to DOL.

(c) Coordinate air porter support of official party for the banquet and hop. Submit USMA form 1-189, transportation request to DOL.

(d) ICW BTD, gather information from Class Committee regarding number of cadets and guests attending the banquet.

(e) Approve banquet seating plan, script, and program by the members of the 2008 Class Committee.

(f) Coordinate for the printing of the banquet programs NLT Wednesday, 17 JAN 07. Provide copies to USCC SGS and USMA Protocol Office.

(g) Supervise table setup in the Cadet Mess by Class Committee representatives from 1500-1700 on Saturday, 20 JAN 2007.

(h) Coordinate for DOIM support for the banquet and the hop. Ensure setup NLT 20 1345 JAN 2007 for the rehearsal.

(i) Coordinate musical support in Eisenhower Hall Ballroom and Benny’s Lounge from 2000-0030, Saturday, 20 JAN 2007 for the hop.

(j) Coordinate for photographer for hop.

(7)  Cadet Hostess.

(a)  Coordinate with the Class Committee of 2008 for the gift for the guest speaker.

(b)  ICW 2nd Regiment, prepare the 500th Night official guest list and invitations. Determine and coordinate cadet escort requirements. Collect RSVPs.

(c) Supervise the Class Committee decoration and setting of the head tables during the banquet.

(8)  ISD.  In coordination with USCC S3 and BTD, develop and implement a web based information signup (2-10 JAN 07) to gather information from second class cadets regarding VIPs and handicapped parking requirements.

(9) USCC Chaplain. Conduct the invocation and benediction during the 500th Night banquet on 20 JAN 2007.

d. 	Coordinating Instructions.

(1) Uniform:

(a) Cadets: Dress Gray

(b) Military Officers and NCOs: Dress Blue

(c) Civilians: Formal attire

(2)  Second Class Privileges for the 500th Night weekend are established and outlined on the internal USCC main web page under AY 06-07 Privilege Memos.

(3) Sequence of events –

Time			Event

Wednesday, 10 JAN

0900			IPR #1 (USCC Conference Room)

Wednesday, 17 JAN

0900			IPR #2 (USCC Conference Room)

Saturday, 20 JAN 2007

1730-1830		Commandant’s Reception

1800			Doors open to Cadet Mess for Banquet

1900			Banquet - Opening remarks by Class President

Invocation

Toasts

Dinner

Introduction of Guest Speaker by Class President

Guest Speaker – TBD

Topic – TBD

Gift presentation to speaker

Benediction

Closing remarks by Class President

Official Party Departs

2030			Receiving lines open

2030			Hop begins

2130			Receiving lines close

0030			Hop closes

Entertainment:  Contract DJ in ballroom

Jazz Knights in Benny Haven’s Room

Photographer 2100-2230, Crest Hall

(4)  Submit after action reports to USCC S3 NLT 01 FEB 2007 in the following format.

Issue

Discussion

Recommendation

4.	SERVICE SUPPORT.

a.	Medical evacuation and hospitalization.

(1)  Cadets.

(a)  Routine care.  The cadet health clinic is open during normal hours, 0600-1500, for routine cadet care.  Cadets should report to the Keller Hospital emergency room if needed during evening and weekend hours.

(b)  Emergency care.  Keller Hospital emergency room.

(2)  Civilian guests.

(a)  Routine care.  Visiting civilian guests or family members can receive routine medical care, if needed, in Cornwall or St. Luke’s Hospital in Newburgh.

(b)  Emergency care.  Keller Hospital emergency room.

b. Parking.

(1) Parking in the cadet area at West Point is prohibited. Parking in the Central Post Area is extremely limited from 7:30 a.m. to 4:30 p.m. However, ample visitor parking is available at Clinton and Thayer lots for the banquet and hop.

(2)  Handicapped Parking.  Handicapped parking will be available in North Area Handicapped parking passes are available through the BTD chain-of-command only. However, vehicles possessing state issued handicapped passes will also be allowed to park in North Area.

(3)  The Commandant’s official guests will be issued North Area parking passes through BTD and be allowed to park their vehicle in North Area on 500th Night from 1600-0030.

5.	COMMAND AND SIGNAL.

a.	Command.  Normal.

b.	Signal.  Activity points of contact.

ACTIVITY					TELEPHONE

USCC S-3						6148

USCC S4						6921

DCA							4396

XO, CMDT					3140

Cadet Mess					5974

2nd Regiment					4405

Cadet Hostess					3104

CASLEN

BG

## OFFICAL:

HOUSTON

S3

ANNEX A – Class Weekend Banquet and Hop Checklist

Transportation

- S4 briefs gate guards on official guests and handicapped parking passes

- Airporters in place to pick up official party at Quarters 100.

  - Drivers briefed on route, urgency, and drop off point

- Mac statue chain down for official party movement

- Buses to take guests to the Hop are ready at Mac statue

Mess Hall Banquet

- DOIM camera, 3 big screens ready to view guest speaker

- Mess Hall audio speakers working

- Podium has two mikes, both working

- Guest Speaker and Class President books ready

- Programs set on tables

- Cadet gift present

- Toasting glasses filled and ready on table near podium

- Colors correct and properly presented

Hop

- Doors open at Eisenhower Hall with DCA rep available

- Receiving lines and colors ready

- Drinks for official party ready

- DJ in Ballroom ready

- Band in Benny’s Lounge ready

- Hostess present